## Sheet1
job_id | jobcard_no | entry_date | target_date | project_name | module_name | task_type | staff_name | call_type | status | status_filter | remarks | problems | create_user_id | edit_user_id | completed_user | completed_date | created_date | Estimated hrs | Worked hrs | points
|  | 2026-04-02 14:53 |  | Blue Planet UK | Setup | New Task | 1008412 | Normal | Completed | Pending |  | Project Setup | 1008412 | 1008412 | 1008412 | 2026-04-02 17:46 | 2026-04-02 14:53 | 03:00 | 02:53:09
|  | 2026-04-04 09:05 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Completed | Pending |  | MIS REPORT - PURCHASE EXPENSE AND INTEGRATED LOG SHEET | 1008412 | 1008412 | 1008412 | 2026-04-04 13:54 | 2026-04-04 09:05 | 04:00 | 04:49:50
|  | 2026-04-11 09:14 |  | Zigma - Task Manager | Ticket entry / Report | New Task | 1008412 | Normal | Completed | Pending |  | Loading Issue - Fix | 1008412 | 1008412 | 1008412 | 2026-04-11 12:55 | 2026-04-11 09:14 | 02:00 | 03:41:21
|  | 2026-04-13 09:44 |  | Blue Planet - India | User Control | Additional | 1008412 | Normal | Completed | Pending |  | Staff Creation - Salary Related Giving Access Via Backend | 1008412 | 1008412 | 1008412 | 2026-04-13 13:33 | 2026-04-13 09:44 | 02:00 | 03:49:03
|  | 2026-04-16 11:05 |  | Blue Planet Biofuels | HR Module | Correction | 1008412 | Normal | Completed | Pending |  | shift roaster datatable mismatch | 1008412 | 1008412 | 1008412 | 2026-04-16 13:30 | 2026-04-16 11:05 | 01:00 | 02:25:28
|  | 2026-04-20 11:08 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Completed | Pending |  | Time Sheet Documentation | 1008412 | 1008412 | 1008412 | 2026-04-20 13:06 | 2026-04-20 11:08 | 01:00 | 01:57:59
|  | 2026-04-24 12:04 |  | Blue Planet Biofuels | All Modules | New Task | 1008412 | Normal | Completed | Pending |  | MENU AND GIT ISSUE | 1008412 | 1008412 | 1008412 | 2026-04-24 14:28 | 2026-04-24 12:04 | 01:00 | 02:24:07
|  | 2026-04-24 15:17 |  | Blue Planet Biofuels | Admin & Master | New Task | 1008412 | Normal | Completed | Pending |  | Customer Creation - API Integration From IWMS In Local | 1008412 | 1008412 | 1008412 | 2026-04-24 16:22 | 2026-04-24 15:17 | 02:00 | 01:04:25
|  | 2026-04-25 10:09 |  | Task Tracker - for KPI | Reports | New Task | 1008412 | Normal | Completed | Pending |  | KPI Excel For Variable Pay | 1008412 | 1008412 | 1008412 | 2026-04-25 14:25 | 2026-04-25 10:09 | 01:30 | 04:15:28
|  | 2026-04-28 16:49 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Completed | Pending |  | Beta To Live TimeSheet | 1008412 | 1008412 | 1008412 | 2026-04-28 17:13 | 2026-04-28 16:49 | 01:00 | 00:23:55
|  | 2026-04-29 15:07 |  | Others | Documentation | New Task | 1008412 | Normal | Completed | Pending |  | fill report | 1008412 | 1008412 | 1008412 | 2026-04-29 15:58 | 2026-04-29 15:07 | 01:30 | 00:50:34
|  | 2026-05-05 12:33 |  | Others | Documentation | Additional | 1008412 | Normal | Completed | Pending |  | Excel documentation work for task management | 1008412 | 1008412 | 1008412 | 2026-05-05 13:50 | 2026-05-05 12:33 | 01:00 | 01:16:21
|  | 2026-05-06 09:22 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Completed | Pending |  | Masters For Integrated,sale and purchase expense - Documentation | 1008412 | 1008412 | 1008412 | 2026-05-06 12:30 | 2026-05-06 09:22 | 01:30 | 03:08:06
|  | 2026-05-07 09:18 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Completed | Pending |  | Purchase Expense Target and also store values in table | 1008412 | 1008412 | 1008412 | 2026-05-07 13:21 | 2026-05-07 09:18 | 06:00 | 04:03:26
|  | 2026-05-21 15:02 |  | Blue Planet Biofuels | Purchase | Additional | 1008412 | Normal | Completed | Pending |  | By default, the pending list should be displayed in the list view Required: Select the “All” option in the list view. | 1008412 | 1008412 | 1008412 | 2026-05-21 15:47 | 2026-05-21 15:02 | 01:00 | 00:45:28
|  | 2026-05-22 09:17 |  | Zigma Payroll | Masters/Entry | Additional | 1008412 | Normal | Completed | Pending |  | Travel Request - Cab Document Upload | 1008412 | 1008412 | 1008412 | 2026-05-22 11:03 | 2026-05-22 09:17 | 01:00 | 01:45:59
|  | 2026-05-26 16:54 |  | Blue Planet Biofuels | Time Sheet | Additional | 1008412 | Normal | Completed | Pending |  | Timesheet Module Additional Filterand Report Calculation For Time Spend | 1008412 | 1008412 | 1008412 | 2026-05-26 17:28 | 2026-05-26 16:54 | 02:00 | 00:33:29
|  | 2026-04-03 10:00 |  | Others | Documentation | New Task | 1008412 | Normal | Pause | Pending |  | Weekly Mail For BP | 1008412 | 1008412 | 1008412 | 2026-04-03 10:22 | 2026-04-03 10:00 | 01:00 | 00:22:03
|  | 2026-04-02 09:22 |  | Blue Planet Biofuels | HR Module | Additional | 1008412 | Normal | Pause | Pending |  | Attendance Report Load Issue and abstract status changes | 1008412 | 1008412 | 1008412 | 2026-04-02 14:49 | 2026-04-02 09:22 | 02:00 | 05:26:50
|  | 2026-04-03 09:10 |  | Blue Planet UK | Setup | New Task | 1008412 | Normal | Pause | Pending |  | Menu Setup and bug fixing | 1008412 | 1008412 | 1008412 | 2026-04-03 09:59 | 2026-04-03 09:10 | 03:00 | 00:50:33
|  | 2026-04-15 09:10 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Data Verification and Fetching Integrated Log | 1008412 | 1008412 | 1008412 | 2026-04-15 13:55 | 2026-04-15 09:10 | 03:00 | 04:17:41
|  | 2026-04-16 09:15 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | MIS Dashboard | 1008412 | 1008412 | 1008412 | 2026-04-16 11:04 | 2026-04-16 09:15 | 04:00 | 05:53:31
|  | 2026-04-17 09:17 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | 1. 1st week starts from 1st april to 5th april and 2nd week start from 6th to 12 (Its monday to sunday) 2. CBG Stock = Last Day value of the selected week Example. 1. If the week is from 1 to 5 CBG Stock = 5th of April stock will reflect 2. If the week is from 6 to 12 CBG stock = 12th of april stock will reflect 3. Total Waste Received = Total Waste (Actual) + Total Waste (Reported) 4. Organic Waste Feed = Organic Feedstock (Digester 1) + Organic Feedstock (Digester 2) 5. Wherever digester 1 and digester 2 is not mentioned just take the total value of organic feedstock | 1008412 | 1008412 | 1008412 | 2026-04-17 15:19 | 2026-04-17 09:17 | 03:00 | 04:07:10
|  | 2026-04-20 09:06 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Purchase Expense Inputs Based On That Report and Dashboard | 1008412 | 1008412 | 1008412 | 2026-04-20 11:04 | 2026-04-20 09:06 | 04:00 | 04:13:19
|  | 2026-04-20 13:12 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | Time Sheet Master For Phrase and main and sub task | 1008412 | 1008412 | 1008412 | 2026-04-20 18:12 | 2026-04-20 13:12 | 03:00 | 02:58:46
|  | 2026-04-21 12:56 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | Time Sheet Assigned Dashboard | 1008412 | 1008412 | 1008412 | 2026-04-21 17:38 | 2026-04-21 12:56 | 04:00 | 04:23:34
|  | 2026-04-21 10:14 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Week No Calculations | 1008412 | 1008412 | 1008412 | 2026-04-21 11:35 | 2026-04-21 10:14 | 03:00 | 01:41:56
|  | 2026-04-22 09:45 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | Time Sheet Fetch Previous Record | 1008412 | 1008412 | 1008412 | 2026-04-22 13:32 | 2026-04-22 09:45 | 02:00 | 03:42:43
|  | 2026-04-24 09:23 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | DROPDOWN BASED ON DEPARTMENT WISE AND USERWISE WHICH IS CREATED IN TIMESHEET PROJECT CREATION | 1008412 | 1008412 | 1008412 | 2026-04-24 15:17 | 2026-04-24 09:23 | 03:00 | 04:32:50
|  | 2026-04-27 09:10 |  | Blue Planet Biofuels | Admin & Master | New Task | 1008412 | Normal | Pause | Pending |  | Customer Creation - API Integration From IWMS Sub Property | 1008412 | 1008412 | 1008412 | 2026-04-27 10:38 | 2026-04-27 09:10 | 03:00 | 01:28:49
|  | 2026-04-27 10:38 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | Master For Phrases and Based On That Need To Show In Timesheet Dashboard | 1008412 | 1008412 | 1008412 | 2026-04-27 17:48 | 2026-04-27 10:38 | 03:00 | 01:47:54
|  | 2026-04-28 09:13 |  | Zigma Payroll | Report | Additional | 1008412 | Normal | Pause | Pending |  | Yearly Leave Report - Wages Filter and Status | 1008412 | 1008412 | 1008412 | 2026-04-28 10:48 | 2026-04-28 09:13 | 02:00 | 01:27:38
|  | 2026-04-29 09:09 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Masters For Target Values Integrated Log Sheet , Purchase Expense and Sale Invoice | 1008412 | 1008412 | 1008412 | 2026-04-29 09:14 | 2026-04-29 09:09 | 03:00 | 00:04:20
|  | 2026-04-29 09:18 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | TimeSheet Report Analysis | 1008412 | 1008412 | 1008412 | 2026-04-29 13:06 | 2026-04-29 09:18 | 01:30 | 03:05:04
|  | 2026-04-29 13:06 |  | Blue Planet Biofuels | Time Sheet | New Task | 1008412 | Normal | Pause | Pending |  | Time Sheet Report | 1008412 | 1008412 | 1008412 | 2026-04-29 13:45 | 2026-04-29 13:06 | 03:00 | 05:00:12
|  | 2026-05-04 09:12 |  | Blue Planet Biofuels | Ticket Management | New Task | 1008412 | Normal | Pause | Pending |  | Ticket management Break Up and Enhancement | 1008412 | 1008412 | 1008412 | 2026-05-04 16:03 | 2026-05-04 09:12 | 04:00 | 03:21:32
|  | 2026-05-05 09:18 |  | Blue Planet Biofuels | Time Sheet | Additional | 1008412 | Normal | Pause | Pending |  | Multi Select Option In Project And Also Modification In Main Task | 1008412 | 1008412 | 1008412 | 2026-05-05 18:02 | 2026-05-05 09:18 | 06:00 | 04:46:38
|  | 2026-05-06 12:31 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Masters For Purchase expense,integrated and sale invoice - Target Values | 1008412 | 1008412 | 1008412 | 2026-05-06 17:59 | 2026-05-06 12:31 | 06:00 | 04:14:29
|  | 2026-05-08 13:10 |  | Blue Planet Biofuels | Time Sheet | Additional | 1008412 | Normal | Pause | Pending |  | Time Sheet Report - User Level Access and Break Up Shown | 1008412 | 1008412 | 1008412 | 2026-05-08 18:09 | 2026-05-08 13:10 | 03:00 | 02:59:53
|  | 2026-05-08 09:16 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | Purchase Expense Sub Category and Calculation for Target | 1008412 | 1008412 | 1008412 | 2026-05-08 13:10 | 2026-05-08 09:16 | 05:00 | 06:34:58
|  | 2026-05-11 09:11 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Purchase Expense Calculation Based on Targets | 1008412 | 1008412 | 1008412 | 2026-05-11 18:10 | 2026-05-11 09:11 | 07:00 | 05:40:27
|  | 2026-05-13 09:15 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Analysis And Purchase Expense Integration Based On Targets | 1008412 | 1008412 | 1008412 | 2026-05-13 10:00 | 2026-05-13 09:15 | 08:00 | 09:32:21
|  | 2026-05-13 10:00 |  | Blue Planet Biofuels | Purchase | Additional | 1008412 | Normal | Pause | Pending |  | Timesheet Entry Sub Task - Multi Fields Functional | 1008412 | 1008412 | 1008412 | 2026-05-13 17:37 | 2026-05-13 10:00 | 02:00 | 02:23:35
|  | 2026-05-13 10:02 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | Based On Requirements Need To Change The Type Options In Mis Report | 1008412 | 1008412 | 1008412 | 2026-05-13 15:05 | 2026-05-13 10:02 | 03:30 | 03:00:52
|  | 2026-05-16 09:09 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | view pop up for Expense Sub Category and validation for total | 1008412 | 1008412 | 1008412 | 2026-05-16 13:30 | 2026-05-16 09:09 | 03:00 | 04:02:21
|  | 2026-05-18 09:07 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | The “Target” column should be adjacent to its respective “Actual” column in the report layout. Please refer to Requirement Tracker, point 265, for the expected arrangement. Implement backend calculations for Target values to reflect in the MIS Report according to the logic in Requirement Tracker – Point No. 265. | 1008412 | 1008412 | 1008412 | 2026-05-18 13:23 | 2026-05-18 09:07 | 05:00 | 03:37:03
|  | 2026-05-19 09:13 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | Implement backend calculations for Target values to reflect in the MIS Report according to the logic in Requirement Tracker – Point No. 265. | 1008412 | 1008412 | 1008412 | 2026-05-19 13:38 | 2026-05-19 09:13 | 06:00 | 05:42:50
|  | 2026-05-20 09:18 |  | Blue Planet Biofuels | MIS - REPORT | Additional | 1008412 | Normal | Pause | Pending |  | revised the backend formula for production targets because the output values were deviating and target values setback | 1008412 | 1008412 | 1008412 | 2026-05-20 12:31 | 2026-05-20 09:18 | 05:00 | 01:51:29
|  | 2026-05-20 12:33 |  | Others | code backup | New Task | 1008412 | Normal | Pause | Pending |  | Schema Backup In Erp | 1008412 | 1008412 | 1008412 | 2026-05-20 15:02 | 2026-05-20 12:33 | 02:00 | 02:39:15
|  | 2026-05-21 09:12 |  | Blue Planet Biofuels | Sales | New Task | 1008412 | Normal | Pause | Pending |  | Sale Invoice Analysis and Documentation | 1008412 | 1008412 | 1008412 | 2026-05-21 15:01 | 2026-05-21 09:12 | 02:00 | 03:05:21
|  | 2026-05-22 11:03 |  | Blue Planet Biofuels | Admin & Master | Additional | 1008412 | Normal | Pause | Pending |  | Customer Additional Fields For Sale Invoice | 1008412 | 1008412 | 1008412 | 2026-05-22 13:36 | 2026-05-22 11:03 | 04:00 | 02:21:58
|  | 2026-05-22 14:26 |  | Blue Planet Biofuels | Sales | Additional | 1008412 | Normal | Pause | Pending |  | Sale Invoice Additional Field For MIS Report | 1008412 | 1008412 | 1008412 | 2026-05-22 17:59 | 2026-05-22 14:26 | 03:00 | 02:33:57
|  | 2026-05-23 09:14 |  | Blue Planet Biofuels | Sales | Additional | 1008412 | Normal | Pause | Pending |  | Sale Invoice Validation and Fields Changes | 1008412 | 1008412 | 1008412 | 2026-05-23 10:10 | 2026-05-23 09:14 | 03:00 | 03:23:20
|  | 2026-05-25 14:53 |  | Others | code backup | New Task | 1008412 | Normal | Pause | Pending |  | schema backup checking in local | 1008412 | 1008412 | 1008412 | 2026-05-25 17:44 | 2026-05-25 14:53 | 01:00 | 08:11:08
|  | 2026-05-28 09:54 |  | Blue Planet Biofuels | Sales | New Task | 1008412 | Normal | Pause | Pending |  | CBG Gas Master Documentation | 1008412 | 1008412 | 1008412 | 2026-05-28 14:31 | 2026-05-28 09:54 | 01:30 | 01:25:57
|  | 2026-05-28 14:32 |  | Blue Planet Biofuels | Sales | New Task | 1008412 | Normal | Pause | Pending |  | CBG Gas Master | 1008412 | 1008412 | 1008412 | 2026-05-28 16:09 | 2026-05-28 14:32 | 05:00 | 04:14:40
|  | 2026-05-29 11:45 |  | Blue Planet Biofuels | Sales | New Task | 1008412 | Normal | Pause | Pending |  | Sale Invoice Validation For CBG Master | 1008412 | 1008412 | 1008412 | 2026-05-29 15:32 | 2026-05-29 11:45 | 03:00 | 03:19:45
|  | 2026-05-29 15:38 |  | Blue Planet Biofuels | All Modules | New Task | 1008412 | Normal | Pause | Pending |  | Data Migrations in all modules | 1008412 | 1008412 | 1008412 | 2026-05-29 18:05 | 2026-05-29 15:38 | 08:00 | 02:26:54
|  | 2026-05-30 09:19 |  | Blue Planet Biofuels | MIS - REPORT | New Task | 1008412 | Normal | Pause | Pending |  | Sale Invoice Analyis To Integrate In MIS Report | 1008412 | 1008412 | 1008412 | 2026-05-30 13:02 | 2026-05-30 09:19 | 02:00 | 02:02:09